## Sheet1
Date | Time | Event | Remarks
June 29 2000 | 16:00-17:30 | Check valves working correctly or not on the ground
July 3 2000 | 9:00-9:50 | Transport tools/Check the numbers of parts carried in to the MIU-4 site
July 3 2000 | 23:25 | Stop drilling at base of the Toki lingnite Fm | 78.02mfrp
July 4 2000 | 8:00-19:30 | Check test tools working correctly or not on the ground
July 4 2000 | 18:00 | Decide packer straddle | For Toki lignite formation : Test interval is 68.45- 78.02 (mfrp) with single packer. Packer position is 66.95-68.45 (mfrp)
For Akeyo Fm:Test interval is 35.2-50.1with double packers. Packer position is 35.1-50.1 (mfrp)
July 5 2000 | 8:00-11:30 | Set tools , preparation for installation
July 5 2000 | 11:30-12:30 | Installation of probe | Took a long time due to setting optical cable orienting along the inclinced borehole
July 5 2000 | 13:30 | Start installation of rods and tubings | Took a long time due to setting optical cable orienting along the inclinced borehole
July 5 2000 | 14:40-15:40 | Check pressure gauges and valves work correctly or not
July 5 2000 | 19:30 | Complete installation of rods and tubings
July 5 2000 | 22:10 | Start packer inflation | Packer interval 66.95-68.45
July 6 2000 | 3:30 | Complete packer inflation
July 6 2000 | 3:32 | Open valve (start COM)) | pressure difference 4m
July 6 2000 | 4:30 | Shut-in valve (start PSR)
July 8 2000 | 15:56 | Complete PSR
July 8 2000 | 16:00 | Start PW1 | pressure difference 10m
July 9 2000 | 11:45 | Complete PW1
July 9 2000 | 13:45 | Start SW | pressure difference 10m
July 9 2000 | 16:15 | Start SWS
July 11 2000 | 2:00 | Complete SWS
July 11 2000 | 3:40 | Start PW2
July 11 2000 | 13:00 | Complete PW2
July 11 2000 | 13:30 | Start PW3 | Remeasurement due to data acquisition problem during PW2
July 12 2000 | 6:20 | Complete PW3
July 12 2000 | 6:40 | Start packer deflation
July 12 2000 | 8:00 | Complete packer deflation
July 12 2000 | 8:50 | Start unistallation of tubings, rods and probe
July 12 2000 | 14:30 | Complete uninstallation
July 13 2000 | 11:00 | Decide packer straddle | For Toki lignite formation(basal conglomerate) : Test interval is 82.50- 88.65 (mfrp) with single packer. Packer position is 81.00-82.50 (mfrp)
July 13 2000 | 13:00-14:30 | Check test tools working correctly or not on the ground
July 13 2000 | 14:30-18:00 | Set tools , preparation for installation
July 14 2000 | 8:00-10:30 | Preparation for installation
July 14 2000 | 10:30-12:00 | Installation of probe | Took a long time due to setting optical cable orienting along the inclinced borehole
July 14 2000 | 12:00-13:00 | Check pressure gauges and valves work correctly or not
July 14 2000 | 13:00 | Start installation of rods and tubings | Took a long time due to setting optical cable orienting along the inclinced borehole
July 14 2000 | 17:00 | Complete installation of rods and tubings
July 14 2000 | 17:00-18:00 | Preparation for packer inflation
July 14 2000 | 18:00 | Start packer inflation
July 15 2000 | 0:55 | Complete packer inflation
July 15 2000 | 2:20 | Open valve (start COM)) | pressure difference 2.9m
July 15 2000 | 6:20 | Shut-in valve (start PSR)
July 15 2000 | 11:30 | Complete PSR
July 15 2000 | 13:10 | Start SW | pressure difference 9.0m
July 15 2000 | 16:00 | Start SWS
July 16 2000 | 9:45 | Complete SWS
July 16 2000 | 10:00-11:00 | Installation of pump
July 16 2000 | 11:00-18:30 | Preparation for water sampling
July 16 2000 | 18:30-20:40 | Water level adjustment
July 16 2000 | 20:40 | Start RW | flow rate 350ml/hr
July 19 2000 | 4:00 | Close main bulve( Start RWS)
July 21 2000 | 21:30 | Complete RWS
July 21 2000 | 22:00 | Start SW2
July 21 2000 | 23:20 | Start SWS2
July 23 2000 | 0:50 | Complete SWS2
July 23 2000 | 1:00 | Start water sampling (RW2) | flow rate 350ml/hr
July 24 2000 | 14:45 | Stop water sampling (RW2)
July 24 2000 | 15:00 | Start packer deflation
July 24 2000 | 15:00-16:00 | Uninstallation of pump
July 24 2000 | 17:00 | Complete packer deflation
July 24 2000 | 18:15-20:00 | Unistallation of tubings
July 25 2000 | 8:20-10:10 | Uninstallation of rods and probe
July 25 2000 | 10:10-16:00 | Cleaning tubings, rods and probe